# Timeline plan (on 29/1/13)
End of January:
Considerations: Exams and coursework may leave me short of time.
Targets:
- Decide on, and have an overall knowledge on, the method of fluid dynamics simulation to use.
- Start work on the mesh code.
End of February:
Targets:
- Make a working demo of the mesh renderer.
- Start a prototype of fluid simulation
End of March:
Targets:
- Create landscape meshes
- Improve on fluid simulation
End of April:
Targets:
- Finish a prototype of fluid simulation
- Assess the result (with initial feedback from others)
End of May:
Considerations: Exams will leave me short of time
Targets:
Improve on fluid simulation (change tack if prototype not successful)
End of June:
Considerations: Exams will leave me short of time
Targets:
- Improve on fluid simulation
- Add fluid effects
- Add mesh scenery
- Assess the result (with feedback from others)
End of July:
Considerations: Summer holidays
Targets:
- Finish fluid simulation
- Polish demo: add effects and decorations
- Look for / try to make some accompanying music?
End of August:
Considerations: Summer holidays
Targets:
Polish demo: add effects
End of September:
Considerations: UCAS applications may leave me short of time
Targets:
Polish demo
October:
Targets:
Polish demo
Final submission by the second week of October

# Timeline plan (on 30/4/13)
(Timeline created 14 January)
End of January:
Considerations: Exams and coursework may leave me short of time.
Targets:
- Decide on, and have an overall knowledge on, the method of fluid dynamics simulation to use. (done)
- Start work on the mesh code. (done)
End of February:
Targets:
- Make a working demo of the mesh renderer. (done)
- Start a prototype of fluid simulation (done, 7 March)
End of March:
Targets:
Improve on fluid simulation (done)
End of April:
Targets:
Research the method of cloth simulation to use (done)
(Timeline revised 30 April from this point onwards)
End of May:
Considerations: Exams will leave me short of time
Targets:
- Implement tessellated grid mesh (est. 6 hours)
- Implement constraints for mesh (est. 6 hours)
- Implement verlet integration (est. 6 hours)
- Create prototype of 3D cloth simulation using above (est. 10 hours)
- Create prototype of 3D fluid simulation using above (est. 4 hours)
End of June:
Considerations: Exams will leave me short of time
Targets:
- Implement camera perspective (est. 6 hours)
- Implement octrees (est. 12 hours)
- Cloth simulation collision detection using octrees (est. 8 hours)
- Assess the result (with initial feedback from others)
End of July:
Considerations: Summer schools will leave me short of time (only two weeks in this month!)
Targets:
- Improve on fluid simulation
- Add fluid effects
- Improve on cloth simulation
- Assess the result (with feedback from others)
End of August:
Targets:
- Finish fluid simulation
- Polish demo: add effects and decorations
- Look for / try to make some accompanying music?
End of September:
Considerations: UCAS applications may leave me short of time
Targets:
Polish demo
October:
Targets:
Polish demo
Final submission by the second week of October

# Timeline plan (final, since 17/6/13)
(Timeline created 14 January)
End of January:
Considerations: Exams and coursework may leave me short of time.
Targets:
- Decide on, and have an overall knowledge on, the method of fluid dynamics simulation to use. (done)
- Start work on the mesh code. (done)
End of February:
Targets:
- Make a working demo of the mesh renderer. (done)
- Start a prototype of fluid simulation (done, 7 March)
End of March:
Targets:
Improve on fluid simulation (done)
End of April:
Targets:
Research the method of cloth simulation to use (done)
(Timeline revised 30 April from this point onwards)
End of May/June:
Considerations: Exams will leave me short of time
Targets:
- Research linear algebra, representing 3D points and transformations as vectors, matrices and quaternions (done)
- Implement grid mesh (est. 6 hours) (done, 8/5/13)
(Timeline revised 17 June from this point onwards)
End of July:
Considerations: Summer schools will leave me short of time (only two weeks in this month!)
Targets:
- Implement verlet integration (est. 6 hours) (done, 28/6/13)
- Create prototype of 3D fluid simulation (est. 4 hours)
End of August:
Considerations: Summer arrangements: I will only have one free week in August
Targets:
- Implement camera perspective (est. 4 hours) (done, 13/8/13)
- Review sources used and start writing up evaluations (started)
End of September:
Considerations: University applications may leave me short of time
Targets:
- Implement a bridge simulation game with verlet integration (done, 14/9/13)
- Assess the result of wave and physics demos with feedback from others (done, 15/9/13)
- Polish demo: add effects and decorations (done, added light effects 27/9/13)
- Prepare presentation (started)
October:
Targets:
- Polish demo
- Finish presentation
Final submission by the second week of October